## NPI Launch Tracker
XYZ University iPSC Cell Line Bank – New Product Introduction (NPI) Tracker
Tracks milestones, cross-functional owners, timelines, and budget for each new product/service line launch
Blue = Input ¦ Black = Formula ¦ Green = Cross-sheet
STATUS LEGEND: | Not Started | In Progress | On Track | At Risk | Delayed | Complete
Product / Service Name | Phase | Owner (PI / Staff) | Cross-Functional Team | Planned Start | Target Launch | Milestone Gate | Status | % Complete | Budget ($) | Spent to Date ($) | Remaining ($) | Budget Var. (%) | Notes / Blockers
Banked iPSC Line – Skin Fibroblast | Phase 1: Feasibility | Wen / XYZ Lab | Neurosurgery, IRB, Biosafety | 2026-06-01 | 2026-12-01 | IRB approval + 3 pilot vials passed QC | In Progress | 25% | 45000 | 8000 | 37000 | -82.22%
Banked iPSC Line – PBMC-derived | Phase 1: Feasibility | XYZ Lab / Core | Hematology, Cell Therapy Core | 2026-07-01 | 2027-02-01 | Protocol validation + GMP-lite SOP | Not Started | 0% | 62000 | 0 | 62000 | -100%
Custom Reprogramming Service | Phase 2: Development | Core Manager | Finance, Legal (IP), QA | 2026-05-01 | 2026-10-01 | SOP final + 2 successful customer runs | On Track | 55% | 28000 | 16000 | 12000 | -42.86%
Characterization Package (STR+Pluri) | Phase 2: Development | QA Lead | Genomics Core, Flow Cytometry | 2026-05-15 | 2026-09-01 | Panel validated; 10 samples tested | On Track | 70% | 15000 | 11000 | 4000 | -26.67%
Exosome Harvest Service | Phase 3: Pilot Launch | Wen | Neurosurgery, Bioengineering | 2026-08-01 | 2027-01-01 | 5 pilot preps; SEC/NTA QC passed | Not Started | 0% | 38000 | 0 | 38000 | -100%
Assembloid Differentiation Service | Phase 3: Pilot Launch | XYZ Lab | Neurosurgery, Stem Cell Institute | 2026-09-01 | 2027-06-01 | 3 customer assembloids delivered | Not Started | 0% | 55000 | 0 | 55000 | -100%
Annual Storage Subscription Launch | Phase 2: Development | Admin / Finance | Facilities, IT, Legal | 2026-06-01 | 2026-08-01 | Contract template + billing system live | In Progress | 40% | 8000 | 3200 | 4800 | -60%
Pharma Licensing Framework | Phase 1: Feasibility | Legal / PI | OTC (Tech Transfer), Finance | 2026-07-01 | 2027-03-01 | IP policy approved; 1 signed agreement | Not Started | 0% | 12000 | 0 | 12000 | -100%
Training & Bench Access Program | Phase 2: Development | Core Manager | Safety, Facilities, Education | 2026-06-15 | 2026-11-01 | Safety training module + 5 paying users | In Progress | 30% | 9500 | 2800 | 6700 | -70.53%
International Distribution Pipeline | Phase 4: Scale | PI / XYZ Lab | Legal, Export Control, Finance | 2027-01-01 | 2027-09-01 | Export license + first EU shipment | Not Started | 0% | 22000 | 0 | 22000 | -100%
PROJECT TOTAL | [7 empty] | 22% | 294500 | 41000 | 253500 | -86.08%
MILESTONE GATE DEFINITIONS (Stage-Gate Framework)
Phase | Gate Name | Exit Criteria | Approver | Typical Duration | Key Documents
Phase 1: Feasibility | Gate 0 – Concept Approval | Scientific rationale + market need confirmed; budget approved | PI + Dept Chair | 4-8 weeks | Concept brief, budget request
Phase 1: Feasibility | Gate 1 – Feasibility Sign-off | Pilot data available; IRB/biosafety path identified; IP cleared | PI + OTC + IRB | 8-16 weeks | Pilot data summary, IRB pre-review
Phase 2: Development | Gate 2 – SOP Validation | SOP v1.0 finalized; QC criteria met in ≥3 internal runs | QA Lead + Core Manager | 12-20 weeks | SOP, QC report, risk assessment
Phase 2: Development | Gate 3 – Pricing Approval | Pricing model reviewed; legal/contract template approved | Finance + Legal + PI | 4-6 weeks | Pricing model (this workbook), contract
Phase 3: Pilot Launch | Gate 4 – Pilot Customer Done | ≥2 external customers served; feedback incorporated | PI + Core Manager | 8-16 weeks | Customer feedback log, adverse event log
Phase 4: Scale | Gate 5 – Full Commercial | Volume target met; financials on track; staff trained | Dept Chair + Finance | Ongoing | Monthly KPI dashboard, P&L summary
BUDGET DASHBOARD (Auto-calculated from NPI table above)
Total Program Budget | 294500
Total Spent to Date | 41000
Remaining Budget | 253500
Budget Utilization Rate | 13.92%
Products in Phase 1 | 3
Products in Phase 2 | 4
Products in Phase 3+ | 3
Products Complete | 0
Average % Complete (all lines) | 22%